## Sheet1
FYP Title: Extraction of blood pressure from ECG signals |  |  | Autumn Term | [10 empty] | Spring Term | [15 empty] | Summer Term
TASK | START | END | 2021-10-25 | 2021-11-01 | 2021-11-08 | 2021-11-15 | 2021-11-22 | 2021-11-29 | 2021-12-06 | 2021-12-13 | 2021-12-20 | 2021-12-27 | 2022-01-03 | 2022-01-10 | 2022-01-17 | 2022-01-24 | 2022-01-31 | 2022-02-07 | 2022-02-14 | 2022-02-21 | 2022-02-28 | 2022-03-07 | 2022-03-14 | 2022-03-21 | 2022-03-28 | 2022-04-04 | 2022-04-11 | 2022-04-18 | 2022-04-25 | 2022-05-02 | 2022-05-09 | 2022-05-16 | 2022-05-23 | 2022-05-30 | 2022-06-06 | 2022-06-13 | 2022-06-20 | 2022-06-27
Research and Understanding
Heart and blood pressure research | 2021-10-25 | 2022-01-09
Wearable technologies survey | 2021-11-29 | 2022-01-09
Denoising + ML research | 2021-10-25 | 2022-01-09
Familiarise with Mind the Gap database | 2021-12-06 | 2022-01-09
Higher Level design implementation decision | 2021-12-17 | 2022-01-10
Implementation of chosen methods
Implementation of CNNs | 2022-01-10 | 2022-02-01
Implementation of CNN | 2022-02-01 | 2022-02-15
Implementation of RNN-LSTM | 2022-02-15 | 2022-03-01
End-to-end testing | 2022-02-22 | 2022-03-08
Performance Testing
Testing methods with 2010 challenge data | 2022-02-15 | 2022-03-15
Testing methods with MIMIC I database | 2022-03-15 | 2022-03-29
Testing methods with MIMIC II database | 2022-03-29 | 2022-04-12
Improvements to chosen methods | 2022-04-05 | 2022-04-30
Assessment Preparation
Presentation on literature review to ZP and ERV | 2021-12-13 | 2021-12-20
Interim Report prep and submission | 2021-12-20 | 2022-01-31
Spring coursework and Summer Exams | 2022-02-07 | 2022-04-14
Final Report writeup and submission | 2022-04-14 | 2022-06-15
Final Presentation prep and due date | 2022-06-13 | 2022-06-27